## modules_choice
Module | Depending Module | Sub-Module | Major/Minor/Mandatory | Description | requirements checklist | To Be Implemented (yes / no) | Done | Stack | Who | Page | Priority (1, 2 or 3) 1 = most urgent | Points (out of 100) | Comments | Total Points | SUM
Mandatory | Devops - backend as a service (Docker can handle this) | autonomous container - Docker | Mandatory | Everything must be launched with a single command line to run an autonomous container provided by Docker | - docker in rootless mode : no bind-mount volumes for production | Yes | no (docker prod not functionnal) | Docker | Fanny | 6 | 2 | 30 |  | 30 | 135
Mandatory |  | Google Chrome Compatibility | Mandatory | Your website must be compatible with the latest stable up-to-date version of Google Chrome | Your website must be compatible with the latest stable up-to-date version of Google Chrome | Yes | Yes | Google Chrome(latest) | Yuko | 6 | 2
Mandatory | Server-Side Pong - Pong Gameplay API | Create an SPA page | Mandatory | SPA architecture, javascript is used to update the content without reloading the page | -Your website must be a single-page application. - The user should be able to use the Back and Forward buttons of the browser | Yes | Yes | Javascript | Yuko | 6 | 3
Mandatory | Front | Front-End Framework | Mandatory | Use pure Vanilla JavaScript OR be altered through the FrontEnd module |  | Yes | Yes |  | Yuko | 6 | 1 |  | no Svelte allowed ?
Mandatory | Database | Back end Framework | Mandatory | Use a framework to build the back end |  | Yes | Yes | Django | Eldar | 6 | 1
Mandatory | Front | Game | Mandatory | Use the Frond End Module or override it with the Graphics Module | - 2 participants minimum for a game - possible to propose a tournament: multiple players (more than 2) who can take turns playing against each other. - must display who is playing against whom - must display the order of the players - registration system: each player must input their alias name at the start of a tournament - aliases will be reset when a new tournament begins EXCEPT if we take module user management, which we do. - matchmaking system: the tournament system organize the matchmaking and announce the next fight - identical paddle speed. participants adhere to the same rules - visual must capture the essence of the original pong | Yes | No | threeJs | Celia | 7 | 2
Mandatory |  | Security concerns | Mandatory | Tackle mandatory security concerns | - - protection against sql injection / xss - https connection - validation for forms and any user input, on the server side - ensure routes are protected for the api - no .env or any secrets on github ! | Yes | No (proteciton against xss, inner html cannot be directly used) | HTTPS (if we have a back end or any other features) | Eldar, Yuko, Fanny | 8 | 2
Web |  | Back end Framework | Major | Use a Framework to build the backend (django) | - use django | Yes | Yes | Django | Eldar | 12 | 0 | 10 |  | 10
Web |  | Front-End Framework | Minor | Use a toolkit to build the frontend (bootstrap) | - Your frontend development must use the Bootstrap toolkit in addition of the vanilla Javascript, and nothing else | Yes | Yes | Bootstrap | Yuko | 12 | 0 | 5 |  | 5
Web |  | Database for Backend | Minor |  | - use PostgreSQL | Yes | Yes | PostgresSQL | Fanny | 12 | 0 | 5 |  | 5
Web |  | Tournament Score in Blockchain | Major |  |  | no |  | Ethereum, Solidity |  | 12 |  | 10 |  | 0
User Management |  | Standard user management | Major |  | ◦ Users can subscribe to the website in a secure way. ◦ Registered users can log in in a secure way. ◦ Users can select a unique display name to play the tournaments. ◦ Users can update their information. ◦ Users can upload an avatar, with a default option if none is provided. ◦ Users can add others as friends and view their online status. ◦ User profiles display stats, such as wins and losses. ◦ Each user has a Match History including 1v1 games, dates, and relevant details, accessible to logged-in users. - duplicate usernames / email at our discretion | Yes | Yes | Django Ninja | Eldar | 13 | 1 | 10 |  | 10
User Management |  | Remote Authentication | Major | OAuth 2.0 authentication with 42 | ◦ Integrate the authentication system, allowing users to securely sign in. ◦ Obtain the necessary credentials and permissions from the authority to enable a secure login. ◦ Implement user-friendly login and authorization flows that adhere to best prac- tices and security standards. ◦ Ensure the secure exchange of authentication tokens and user information between the web application and the authentication provider. | Yes | Yes | Oauth42 + authentification system | Fanny | 14 | 2 | 10 |  | 10
Gameplay and user experience |  | Remote Players | Major |  | - Each player is located on a separated computer, accessing the same website and playing the same Pong game. - think about network issue | Yes | No | WebSocket or IoSocker |  | 15 | 2 | 10 |  | 10
Gameplay and user experience |  | Multiplayers | Major |  | - each player needs a live control - define how the game could be played - you can choose a single number of players | No |  | WebSocket or IoSocker |  | 15 | 1 | 10 |  | 0
Gameplay and user experience |  | Game with User History and Matchmaking | Major | Add Another Game with User History and Matchmaking | ◦ Develop a new, engaging game to diversify the platform’s offerings and enter- tain users. ◦ Implement user history tracking to record and display individual user’s game- play statistics. ◦ Create a matchmaking system to allow users to find opponents and participate in fair and balanced matches. ◦ Ensure that user game history and matchmaking data are stored securely and remain up-to-date. ◦ Optimize the performance and responsiveness of the new game to provide an enjoyable user experience. Regularly update and maintain the game to fix bugs, add new features, and enhance gameplay | No |  | WebSocket or IoSocker |  | 15 | 2 | 10 |  | 0
Gameplay and user experience |  | Game Customization | Minor | the goal is to provide customization options for all available games on the platform | ◦ Offer customization features, such as power-ups, attacks, or different maps, that enhance the gameplay experience. ◦ Allow users to choose a default version of the game with basic features if they prefer a simpler experience. ◦ Ensure that customization options are available and applicable to all games offered on the platform. ◦ Implement user-friendly settings menus or interfaces for adjusting game pa- rameters. ◦ Maintain consistency in customization features across all games to provide a unified user experience | Yes | No | threeJs | Celia | 15 | 3 | 5 |  | 5
Gameplay and user experience |  | Live Chat | Major |  | ◦ The user should be able to send direct messages to other users. ◦ The user should be able to block other users. This way, they will see no more messages from the account they blocked. ◦ The user should be able to invite other users to play a Pong game through the chat interface. ◦ The tournament system should be able to warn users expected for the next game. ◦ The user should be able to access other players profiles through the chat in- terface. | Yes | No | Django Channels | Eldar | 16 | 2 | 10 |  | 10
AI-Algo | Game Customization | AI Opponent | Major |  | ◦ Develop an AI opponent that provides a challenging and engaging gameplay experience for users. ◦ The AI must replicate human behavior, meaning that in your AI implemen- tation, you must simulate keyboard input. The constraint here is that the AI can only refresh its view of the game once per second, requiring it to anticipate bounces and other actions. - The AI must utilize power-ups if you have chosen to implement the Game customization options module ◦ Implement AI logic and decision-making processes that enable the AI player to make intelligent and strategic moves. ◦ Explore alternative algorithms and techniques to create an effective AI player without relying on A*. ◦ Ensure that the AI adapts to different gameplay scenarios and user interac- tions. | Yes | No | the AI must utilize power ups if we chose to implement the game customization module | Celia | 17 | 3 | 10 |  | 10
Gameplay and user experience | Game Customization | User and Game Stats Dashboards | Minor |  | ◦ Create user-friendly dashboards that provide users with insights into their own gaming statistics. ◦ Develop a separate dashboard for game sessions, showing detailed statistics, outcomes, and historical data for each match. ◦ Ensure that the dashboards offer an intuitive and informative user interface for tracking and analyzing data. ◦ Implement data visualization techniques, such as charts and graphs, to present statistics in a clear and visually appealing manner. ◦ Allow users to access and explore their own gaming history and performance metrics conveniently. ◦ Feel free to add any metrics you deem useful. | Yes | No | Css/HTML | Yuko | 17 | 3 | 5 |  | 5
Cybersecurity |  | WAF/ModSecurity & Vault | Major | Implement WAF/ModSecurity with Hardened Configuration and HashiCorp Vault for Secrets Management |  | no |  |  |  | 19 |  | 10 |  | 0
Cybersecurity |  | GDPR Compliance | Minor | GDPR Compliance Options with User Anonymization, Local Data Management, and Account Deletion |  | no |  |  |  | 19 |  | 5 |  | 0
Cybersecurity |  | Implement Two-Factor Authentication (2FA) and JWT | Major |  | ◦ Implement Two-Factor Authentication (2FA) as an additional layer of security for user accounts, requiring users to provide a secondary verification method, such as a one-time code, in addition to their password. ◦ Utilize JSON Web Tokens (JWT) as a secure method for authentication and authorization, ensuring that user sessions and access to resources are managed securely. ◦ Provide a user-friendly setup process for enabling 2FA, with options for SMS codes, authenticator apps, or email-based verification. ◦ Ensure that JWT tokens are issued and validated securely to prevent unau- thorized access to user accounts and sensitive data | Yes | Yes |  | Eldar and Fanny | 20 | 4 | 10 |  | 10
Devops |  | Log Management | Major | Infrastructure Setup for Log Management |  | no |  | ELK |  | 21 |  | 10 |  | 0
Devops |  | Monitoring System | Minor |  |  | no |  | Prometheus and Grafana |  | 21 | 4 | 5 |  | 0
Devops |  | Backend as Microservices | Major |  |  | no (most complicated module) |  |  |  | 22 |  | 10 |  | 0
Graphics |  | 3D Techniques | Major |  | - immersive - advanced 3D tehcniques | Yes | No | ThreeJs | Celia | 24 | 2 | 10 |  | 10
Accessibility |  | Device Support | Minor |  |  | no |  |  |  | 25 |  | 5 |  | 0
Accessibility |  | Browser Compatibility | Minor | Expanding Browser Compatibility |  | Yes | Yes | vite + babel |  | 25 |  | 5 |  | 5
Accessibility |  | Multiple Language Supports | Minor | English, Spanish, German |  | no |  |  |  | 26 | 4 | 5 |  | 0
Accessibility |  | Visually Impaired Users | Minor |  |  | no |  |  |  | 26 | 4 | 5 |  | 0
Accessibility |  | Server-Side Rendering (SSR) | Minor |  |  | no |  |  |  | 26 |  | 5 |  | 0
Server-Side Pong |  | Pong Gameplay API | Major | Replacing Basic Pong with Server-Side Pong and Implementing an API |  | no |  | API |  | 27 |  | 10 |  | 0
Server-Side Pong |  | Pong via CLI | Major | Enabling Pong Gameplay via CLI against Web Users with API Integration |  | no |  | API |  | 27 |  | 10 |  | 0

## database (API)
All the data for display of the user profile |  |  | (Can get by game_id) |  |  | GET (For tournament menu)
USER | TYPE |  | MATCH |  |  | paginate / filter by status (pending OR all) |  |  |  | ROUND
username | string |  | winner | USER_PREVIEW |  | TOURNAMENTS |  |  |  | number | int
nickname | string |  | loser | USER_PREVIEW |  | tounaments | [ TOURNAMENT_PREVIEW ] |  |  | brackets | [BRACKET]
date_joined | datetime |  | winner_score | int | [5 empty] | status | string | pending ¦ ongoing ¦ finished
friends | [USER_PREVIEW] |  | loser_score | int
elo | int |  | date | datetime
avatar | string
is_online | bool |  |  |  |  | TOURNAMENT_PREVIEW |  |  |  | BRACKET
total_matches | int |  | Representation of a match for the player page |  |  | name | string |  |  | participant1 | PARTICIPANT
wins | int |  | PLAYER_MATCH |  |  | id | string |  |  | participant2 | PARTICIPANT
loses | int |  | date | datetime |  | date | null ¦ datetime |  |  | winner | null ¦ PARTICIPANT
match_history | [PLAYER_MATCH] |  | elo_change | int |  | status | string | pending ¦ ongoing ¦ finished |  | status | string | pending ¦ ongoing ¦ finished ¦ canceled
elo_history | [ELO_DATA_POINT] |  | opponent | USER_PREVIEW |  | creator | USER_PREVIEW |  |  | game_id | game_id
[6 empty] | tournament_creator | PARTICIPANT
winrate | int |  | score | string |  | required_participants | int | 4 ¦ 8 |  | score_p1 | int
worst_enemy | USER_PREVIEW |  | is_winner | bool |  | participants_count | null ¦ int |  |  | score_p2 | int
[6 empty] | winner | null ¦ PARTICIPANT |  |  | winners_score | int
best_enemy | USER_PREVIEW |  | game_id | string |  | settings | SETTINGS |  |  | losers_score | int
scored_balls | int
is_blocked_user | bool | [8 empty] | PARTICIPANT
is_blocked_by_user | bool |  | Specific point of elo history of a User | [6 empty] | profile | USER
is_friend | bool |  | ELO_DATA_POINT |  |  | GET (can get by tournament_id) |  |  |  | alias | string
title | string |  | day | date |  | TOURNAMENT |  |  |  | status | string | pending ¦ playing ¦ qualified ¦ eliminated ¦ winner | qualified = won the current round and is waiting the next one
price | int |  | daily_elo_change | int |  | name | string | [5 empty] | winner = champion
tournament_history | [TOUNAMENTS] | not implemented yet | elo_result | int |  | id | string |  |  | round??? | int | ???
[6 empty] | date | datetime |  |  | tournament_id | UUID | ???
[6 empty] | status | string | pending ¦ ongoing ¦ finished
[6 empty] | creator | USER_PREVIEW
[6 empty] | tournament_creator | PARTICIPANT
[6 empty] | required_participants | int | 4 ¦ 8
add connection type to user on database : github, 42_, regular | [5 empty] | participants | [PARTICIPANT] |  |  | OPTIONS
[6 empty] | winner | null ¦ PARTICIPANT |  |  | score_to_win | int
[6 empty] | rounds | [ROUND] |  |  | game_speed | string
[6 empty] | settings | SETTINGS |  |  | ranked | bool
For Setting page | [9 empty] | time_limit | int
[10 empty] | cool_mode | bool
username | string
nickname | string |  |  |  |  | POST
email | string |  |  |  |  | TOURNAMENT_REGISTRATION
avatar | string |  |  |  |  | tournament_id | string |  | ?
connection_type | string
mfa_enabled | bool
Brief preview of a user |  |  | Endpoints related to the live chat
USER_PREVIEW |  |  | GET /api/chat/ | paginated
username | string |  | CHAT
nickname | string |  | chats | [CHAT_PREVIEW]
elo | int
avatar | string |  | CHAT_PREVIEW
is_online | bool |  | chat_id | string
|  |  | username | string
|  |  | nickname | string
|  |  | avatar | string
Brief preview of a user |  |  | is_online | bool
SELF_PREVIEW |  |  | unread_messages_count | int
username | string |  | last_message | MESSAGE
nickname | string |  | is_blocked_user | bool
elo | int |  | is_blocked_by_user | bool
avatar | string
is_online | bool |  | GET /api/chat/{username}
unread_messages_count | int |  | CHAT
unread_notifications_count | int |  | chat_id | string
game_id | string |  | username | string
tournament_id | string |  | nickname | string
is_engaged_in_game | bool |  | avatar | string
|  |  | is_online | bool
|  |  | is_blocked_user | bool
|  |  | is_blocked_by_user | bool
|  |  | messages | [MESSAGE]
|  |  | GET /api/chat/{username}/messages | paginated
MESSAGE
|  |  | content | string
|  |  | date | datetime
|  |  | sender | string
|  |  | is_read | bool
|  |  | is_liked | bool
|  |  | id | string
Endpoint related to the notifications
GET /api/notifications
NOTIFICATIONS
|  |  | notifications | [NOTIFICATION]
NOTIFICATION
|  |  | id | string
|  |  | action | string | game_invite, new_tournament, OR new_friend
|  |  | data | GAME_INVITE ¦ NEW_TOURNAMENT ¦ NEW_FRIEND
|  |  | is_read | bool
|  |  | date | datetime
GAME_INVITE
|  |  | game_id | string
|  |  | username | string
|  |  | nickname | string
|  |  | avatar | string
NEW_TOURNAMENT
|  |  | tournament_id | string
|  |  | tournament_name | string
|  |  | username (organizer) | string
|  |  | nickname | string
|  |  | avatar | string
NEW_FRIEND
|  |  | username | string
|  |  | nickname | string
|  |  | avatar | string

## Live Chat protocol (ws)
Websocket endpoint | /livechat/{username} |  | Server --> Client
| example: |  | Chat
| { |  | action | new_message |  | action | like_message |  | action | unlike_message
| "action": "message", |  | data | chat_id | string | data | chat_id | string | data | chat_id | string
| "data": { |  |  | id | string |  | id | string |  | id | string
| "chat_id: "an0355753", |  |  | content | string
| "id": "123", |  |  | date | datetime
| "content": "Hello!", |  |  | sender (username) | string
| "date": "2025-03-06T06:57:39.109Z", |  |  | is_read | bool
| "sender": "pedro2", |  |  | is_liked | bool
"is_read": false,
"is_liked": false,
| } |  | Game notifications
| } |  | action | game_invite |  | action | game_invite_canceled |  | action | game_accepted |  | action | game_declined |  | PROFILE_PREVIEW
| Chat | message | data | username | string | data | client_id | string | data | game_id | string | data | inviter | PROFILE_PREVIEW | username
|  | like_message |  | nickname | string |  | message | string ¦ null |  | inviter | PROFILE_PREVIEW |  | invitee | PROFILE_PREVIEW | nickname
|  | unlike_message |  | avatar | string |  | username | string ¦ null |  | invitee | PROFILE_PREVIEW |  |  |  | avatar
|  | read_message |  |  |  |  | nickname | string ¦ null
|  | edit_message ? | [7 empty] | username | string |  | username | string
|  | delete_message ? | [7 empty] | nickname | string |  | nickname | string
[10 empty] | avatar | string
| Game notifications | game_invite
reply_game_invite
Tounament notifications
|  |  | type | new_tournament |  | type | tournament_finished
| Tounament notification | new_tournament | data | tounament_id | string | data | tounament_id | string
|  |  |  | tournament_name | string |  | tournament_name | string
| Add friend notification | new_friend |  | creator(alias) | string |  | winner(alias) | string
|  |  |  | nickname (organizer ) | string
| Online status | user_online
user_offline
Add friend notification
|  |  | action | new_friend
|  |  | data | username | string
|  |  |  | nickname | string
Online status
|  |  | action | user_online |  | action | user_offline
|  |  | data | username | string | data | username | string
Client -> server
Chat
|  |  | action | new_message |  | action | like_message |  | action | unlike_message |  | action | read_message
|  |  | data | chat_id | string | data | chat_id | string | data | chat_id | string | data | chat_id | string
|  |  |  | content | string |  | id | string |  | id | string |  | id | string
Game notifications
|  |  | action | game_invite |  | action | cancel_game_invite |  | action | reply_game_invite |  |  | OPTIONS
|  |  | data | username | string | data | username | string | data | username | string |  | score_to_win | int
|  |  |  | options | OPTIONS |  |  |  |  | accept | bool |  | game_speed | string
|  |  |  | client_id | string | [7 empty] | ranked | bool
[13 empty] | time_limit | int
[13 empty] | cool_mode | bool
|  |  | Notifications | [9 empty] | * Only selected ones are included.
|  |  | action | read_notification
|  |  | data | id | string

## Tournament protocol (ws)
format: |  | /ws/tournament/{id}
{ |  | Client -> Server |  |  |  | ROUND |  |  | max length
"action": "tournament_start", | [5 empty] | number | int |  | tournament_name: 50
"data": { }, |  | When | The tournament is canceled by creator |  |  | brackets | [ BRACKET ] |  | alias: 12
} |  | To whom | All participants registered in the tournament | [5 empty] | required_participants: 4 ¦ 8
|  | action | tournament_canceled |  |  | BRACKET
|  | data | tournament_id | string |  | match_id | string
|  |  | tournament_name | string |  | participant1 | { PROFILE, alias }
[6 empty] | participant2 | { PROFILE, alias }
| UI | Tounament page | Display the tournament as cancelled
|  | When | New user registration |  |  | winner | { PROFILE, alias } | null if not finished
|  | To whom | All participants registered in the tournament |  |  | score_p1 | int
|  | action | new_registration |  |  | score_p2 | int
|  | data | alias | string
|  |  | avatar | string
| UI | Tounament page | Add new participant to UI
|  | When | Someone is unregistered
|  | To whom | All participants registered in the tournament
|  | action | registration_canceled
|  | data | alias | string
| UI | Tounament page | Remove the unregistered participant from UI
|  | When | The tournament starts
|  | To whom | All participants registered in the tournament
|  | action | tournament_start
|  | data | tournament_id | string
|  |  | tournament_name | string
|  |  | round | ROUND
| UI | Tounament page | Display tournament starting message, then the bracket of round 1
Countdown
Redirect to Multiplayer-game page
|  | When | The round starts | EXCEPT the 1st round
|  | To whom | All qualified participants from the previous round
|  | action | round_start
|  | data | tournament_id | string
|  |  | tournament_name | string
|  |  | round | ROUND
| UI | Tounament page | Display the bracket of the next round
Countdown
Redirect to Multiplayer-game page
|  | When | The user finished his own match
|  | To whom | Both players in the match
|  | action | match_finished |  | --> Which socket sends this: tournament OR pong?
|  | data | tournament_id | string
| UI | Redirect Multiplayer-game page --> the tournament page using tournament_id
|  | When | Each time a match in the current round finished
|  | To whom | All qualified participants
|  | action | match_result
|  | data | tournament_id | string
|  |  | round_number | int
|  |  | bracket | BRACKET
| UI | Tounament page | Display the result of finished match to the participants who had already their own matches and is waiting for others in this page
When all matches finished, launch a "round finished" animation
|  | When | All matches of the current round finished
|  | To whom | All qualified participants
|  | action | round_end
|  | data | tournament_id | string
|  |  | round | ROUND
| UI | Tounament page | nothing
|  | Other pages | Show pop-up alert message to invite the particpants to come back to the tournament page
This alert contains a link to the tounament page
|  | When | At the end of tournament
|  | To whom | Everyone --> via livechat ws (eliminated participants close tournament ws on elimination in order to be able to participate in another one)?
|  | action | tournament_end
|  | data | tournament_id | string
|  |  | winner alias | string
|  |  | winner avatar | string
| UI |  | Show toast notification?

## Tournament flow
Requirement
The tournament will consist of multiple players who can take turns playing against each other.
You have flexibility in how you implement the tournament, but it must clearly
display who is playing against whom and the order of the players.
• A registration system is required:
At the start of a tournament, each player must input their alias name. The aliases will be reset when a new tournament begins.
However, this requirement can be modified using the Standard User Management module.
• There must be a matchmaking system:
The tournament system organize the matchmaking of the participants, and announce the next fight.
Flow
Client side |  |  |  | Server side
Organizer |  | Participants
Create a new tournament | Tournament menu page
New WebSocket connection to an endpoint "tournament" |  |  |  | Accept the connection and create a new tournament room
Navigated to Tounament page (waiting) | Tournament page
Send notification to all connected users (Use 'ws/events', action 'new_tournament')
|  | Those who would like to participate in the tournament go to Tournament Menu page and register (enter alias name). | Tournament menu page
On register button click, open new Websocket connection to an endpoint "tournament"
Accept the connection and the user is added to room.
|  | Redirected to Tournament page where they must stay. Leaving from the page means cancel subscription. | Tournament page
When the required number of participants is reached, a message is sent to everyone via WebSocket (tournament)
Show all pairs of the round and start countdown (5 seconds?)
After 5? seconds, they are redirected to Game |  |  | Game
Start Game
After each game, members come back to Tournament page (Loosers can leave from the tournament) |  |  | Tournament page
At the end of each Game, all participants receive the result of each match via WebSocket
Show the results of finished matched of the round
When all games of the ongoing round finished, a message is sent to everyone via WebSocket to launch a new countdown
Start countdown (5 seconds?)
After 5? seconds, they are redirected to Game |  |  | Game
Repeat until the final round
At the end of the tournament, show the result in tree |  |  | Tournament page
WebSocket related considerations
1. The client opens a socket to /ws/tournament/ and sends a “create_tournament” request.
2. The server generates a new tournament room
3. The server sends back a “tournament_created” action with tournament_id on the socket /ws/tournament . Then, the client closes /ws/tournament and connects to /ws/tournament/(tournament id).
4. The server broatcasts new_tournament action on /ws/events.
5. The participants connect to /ws/tournament/(tournament id).
6. The server adds them to /ws/tournament/(tournament id) group.
7. At the beginning of each round, the participants receive the information about endpoint on /ws/tournament/(tournament id) and connect to the specific endpoint to a match `/ws/tournament/(tournament id)/(match id)`
OR Each round and individual match is managed via server-side groups. (an ordered list of rounds: Round N = array of match-pairs (e.g. player A vs. player B).
- Allias should be unique
- Server should do matchmaking for the next round at the end of the current round (according the subject requirement).
- Clients will stay connected to /ws/tournament/{tournament_id} for the duration of the tournament.
UI
Tournament menu page
- List of tournaments --> On click, registration form with alias
- New tournament creation form

## Tournament game organisation
CASE 1 : one Disconnection | Round 1 | Disconnection | Winners |  | Round 2 | Disconnection | Winner |  |  | One player disconnected |  | Data needed
Bracket 1 | Player 1 | DECO | LOSE | [6 empty] | 10 seconds to reconnect : Player 1 is disconnected and Player 2 is the bracket winner |  | GameRoom | bool | isTournamentRoom
| Player 2 | HERE | WIN | [8 empty] | Bracket | status | CANCELLED
|  |  |  | Final Match | Player2 | HERE | WIN
[5 empty] | Player3 | HERE | LOSE
Bracket 2 | Player 3 | HERE | WIN
| Player 4 | HERE | LOSE
CASE 2 : two disconnections in the same match | Round 1 | Disconnection | Winners |  | Round 2 | Disconnection | Winner |  |  | 2 players disconnected in the same match
Bracket 1 | Player 1 | DECO | LOSE | [6 empty] | The first perceived Disconnection is declared loser, the other is winner.
| Player 2 | DECO | WIN
|  |  |  | Final Match | Player2 | DECO | LOSE |  |  | Before loading the next match, verification if both users are connected. If only one, the connected one is declared winner
[5 empty] | Player3 | HERE | WIN
Bracket 2 | Player 3 | HERE | WIN
| Player 4 | HERE | LOSE
CASE 3 : everybody disconnected on a 4 players tournament | Round 1 | Disconnection | Winners |  | Round 2 | Disconnection | Winner |  |  | All players disconnected
Bracket 1 | Player 1 | DECO | LOSE | [6 empty] | The first perceived Disconnection is declared loser, the other is winner.
| Player 2 | DECO | WIN
|  |  |  | Final Match | Player2 | DECO | LOSE | Tournament Cancelled |  | Before loading the next match, verification if both users are connected. If none and it was the last Bracket, Tournament is cancelled. |  | Last Bracket ? | YES | Tournament Cancelled
[5 empty] | Player3 | DECO | LOSE | [5 empty] | NO | Bracket Cancelled
Bracket 2 | Player 3 | DECO | WIN
| Player 4 | DECO | LOSE
CASE 4 : everybody disconnected on a 8 players tournament | Round 1 | Disconnection | Winners |  | Round 2 | Disconnection | Winners |  | Round 3 | Disconnection | Winner |  |  | All players disconnected
Bracket 1 | Player 1 | DECO | LOSE | [10 empty] | The Game is considered cancelled
| Player 2 | DECO | WIN
Bracket 2 | Player 3 | DECO | WIN |  | Player 2 | DECO | Game Cancelled
| Player 4 | DECO | LOSE |  | Player 3 | DECO
|  |  |  | 2nd match |  |  |  | Final Match | cancelled | CANCELLED | LOSE | Tournament Cancelled
[9 empty] | cancelled | CANCELLED | LOSE |  |  | Before loading the next match, verification if last matches were not cancelled. If both were cancelled and it was the last Bracket, Tournament is cancelled.
Bracket 3 | Player 5 | DECO | LOSE |  | Player 6 | DECO | Game Cancelled
| Player 6 | DECO | WIN |  | Player 7 | DECO
Bracket 4 | Player 7 | DECO | WIN
| Player 8 | DECO | LOSE
[5 empty] | Last Bracket ? | YES | Tournament Cancelled
[6 empty] | NO | Game Cancelled
CASE 5 : one bracket canceled | Round 1 | Disconnection | Winners |  | Round 2 | Disconnection | Winners |  | Round 3 | Disconnection | Winner
Bracket 1 | Player 1 | DECO | LOSE
| Player 2 | DECO | WIN
Bracket 2 | Player 3 | HERE | WIN |  | Player 2 | DECO | LOSE
| Player 4 | HERE | LOSE |  | Player 3 | HERE | WIN
|  |  |  | 2nd match |  |  |  | Final Match | Player 3 | HERE | WIN
[9 empty] | Player 5 | DECO | LOSE
Bracket 3 | Player 5 | HERE | WIN |  | Player 5 | DECO | WIN
| Player 6 | HERE | LOSE |  | Player 7 | DECO | LOSE
Bracket 4 | Player 7 | HERE | WIN
| Player 8 | HERE | LOSE

## game
| Default mode | Features
Ball start position | From a player | REVOLVER that can shoot | CORE feature
| NO customization | Classes: players can have a class that have different characteristics | Customizable: can turn them off or on
|  | Powerups thag you gain from shooting random coins: getting wider, narrower, wall that covers 1/3rd of the town or something else | Customizable: can choose different powerups
|  | Customize ball speed | Customizable: yeah
Whoever scores 10 points wins
Controls with AD
Remote players
Local players
Coin flip at the start
Implement user-friendly settings menus or interfaces for adjusting game parameters | N/A

## front_architecture
process | Pages on website / homes on threeJs | 3D | reached from the hub(game) | components | Figma done | mandatory | Description | Elements | Front done | Back done | background img
1 | Landing Page |  | no | - login button - register button - background - message - mascotte If loggedin, ENTER button instead of Login/Register | Yes |  |  |  | yes
2 | Login Form |  | no | - username - password | Yes
2 | Register From |  | no | - username - password - email | Yes |  | no photo applied here, default picture is applied, random avatar if motivated
3 | start |  | no | - enter the game button - navbar
3 | Home (hub) |  |  | - Button to Profile? - Button to Setting? - Button to Tournament - Button to Dual Navbar hover-to-show?
4 | Profile |  | yes | - Tournament history - Dual history - friends list with status ( connected or not) - searchbar by user name to find friends - Win rate (graph & numbers) - Played games - Number of friends
4 | Settings | no | yes | - change picture - update password - update username (limit ? ) - update email
4 | Tournament | no | yes | - enter alias for tournament - waiting for players ( count of the already connected players)
4 | Play Game |  |  | - Select player (friend or IA)
5 (Normal mode) 6 (from tournament) | TwoPlayersGame | yes | yes | - playGame - leaveGame |  |  | the pong
5 | IAGame |  | yes
5 | matchmaking | no | reached from tournament | - my username - the opponent username |  |  | Myname appears on the left. when the system has found another opponent, the name of the other appears. the match starts
5 | updatePassword | no |  |  |  | X | password is known, the user chooses to change it
5 | resetPassword | no | Link from Settings |  |  |  | password is forgotten. a link must be sent to the email adress. check with django the possibilities
Chat?
Other components
| Navbar: |  |  | - NabBrand (logo) with link to Home or Landing view - Avatar with dropdown menu [Login, Sign up, Theme toggle] or [Profile, Setting, Theme toggle, Logout]
Website name?

## Duel flow
Server | User1 |  |  | User2 |  |  | Server | User1 |  |  | User2
| Game invitation |  | duel-menu |  |  | any page |  | Matchmaking |  | duel-menu | Matchmaking |  | duel-menu
Create a new Duel | waiting |  | duel(inviting) |  |  |  | matchmaking | matchmaking |  | duel(matchmaking) | matchmaking |  | duel(matchmaking)
Receive notification
| Wait | Cancel | [5 empty] | Wait | Cancel |  | Wait | Cancel
|  | cancelled |  | Accept | Decline |  |  |  | cancelled |  |  | cancelled
| starting |  | duel(starting) | starting | cancelled | duel(starting)
[7 empty] | matched |  |  | duel(starting) |  |  | duel(starting)
| Countdown (5sec) | Cancel |  | Countdown (5sec) | Cancel |  | new duel | Countdown (5sec) | Cancel |  | Countdown (5sec) | Cancel
| playing | cancelled |  | playing | cancelled |  |  | playing | cancelled |  | playing | cancelled
|  |  | GAME |  |  | GAME |  |  |  | GAME |  |  | GAME
| Play |  |  | Play |  |  |  | Play |  |  | Play
| End of the duel |  | duel(finished) | End of the duel |  | duel(finished) |  | End of the duel |  | duel(finished) | End of the duel |  | duel(finished)
| finished |  |  | finished |  |  |  | finished |  |  | finished
|  |  | If canceled, duel(cancelled) |  |  | If canceled, duel(cancelled) |  |  |  | If canceled, duel(cancelled) |  |  | If canceled, duel(cancelled)

## App name
proposer | App name Proposals | Votes
|  | Fanny | Eldar | Celia | Yuko | Melodie | Total votes
Fanny | BeetleBash | FALSE | TRUE | TRUE | FALSE | FALSE | 2
Fanny | PythonPong | FALSE | FALSE | FALSE | FALSE | FALSE | 0
Fanny | pongja | FALSE | FALSE | FALSE | FALSE | FALSE | 0
Eldar | Ponggers | FALSE | TRUE | TRUE | TRUE | FALSE | 3
Eldar | Ponggers: BeetleBash | FALSE | FALSE | FALSE | FALSE | FALSE | 0
Eldar | Cowbug Ponggers | FALSE | FALSE | FALSE | TRUE | FALSE | 1
Celia | Coleopong | FALSE | TRUE | FALSE | TRUE | FALSE | 2
Celia | Peacemakers : Ponggers edition | TRUE | TRUE | TRUE | FALSE | TRUE | 4
Celia | The Good, the Beetle, and the Robot | FALSE | TRUE | FALSE | FALSE | FALSE | 1
Yuko | CowBug Pong | FALSE | TRUE | FALSE | TRUE | TRUE | 3
Yuko | Pistolero Pong | FALSE | FALSE | FALSE | FALSE | FALSE | 0
Yuko | Pistobug Pong | TRUE | FALSE | FALSE | FALSE | FALSE | 1
Melodie | Lucky Pong | FALSE | FALSE | FALSE | FALSE | FALSE | 0
Melodie | Guns & Pongers | TRUE | TRUE | FALSE | FALSE | FALSE | 2
Melodie | Flaming Pong | FALSE | FALSE | FALSE | FALSE | FALSE | 0

## meeting_24
profile picture | a set of 10 differents drawed insect avatars ? | profile picture retrieved from github or 42 ?
| for regular connection | for oaut2